## Q4-1.2
Q.4.1.2
Activity | Description | Predecessor | Time (Days) | ES | EF | LS | LF | Slack
A | Choose Items (department Managers) | - | 3 | 0 | 3 | 0 | 3 | 0
B | Choose Items (Buyers) | - | 2 | 0 | 2 | 1 | 3 | 1
C | Choose and Price items for ad | A,B | 2 | 3 | 5 | 3 | 5 | 0
D | Prepare Art | C | 4 | 5 | 9 | 5 | 9 | 0
E | Prepare Copy | C | 3 | 5 | 8 | 8 | 11 | 3
F | Design Avertisement | D,E | 2 | 9 | 11 | 14 | 16 | 5
G | Compile Mailing list | C | 3 | 5 | 8 | 12 | 15 | 7
H | Print Labels | G | 1 | 8 | 9 | 15 | 16 | 7
I | Print advertisement | F | 5 | 11 | 16 | 11 | 16 | 0
J | Affix labels | H,I | 2 | 16 | 18 | 16 | 18 | 0
K | Deliver advertisements | J | 10 | 18 | 28 | 18 | 28 | 0
Critical Path
A-C-D-I-J-K
26
Minimum time taken for project completion is 26 days

## Q4-2.1
Q.4.2.2 | Time Estimates (Days)
Task | a | m | b | Time (t) | Mean Variance (v) | Activity | Predecessor | Time (Days) | ES | EF | LS | LF | Slack
A | 2 | 3 | 6 | 3.3333 | 0.44444 | A | - | 3.3333 | 0 | 3.3333 | 0 | 3.3333 | 0
B | 2 | 2 | 2 | 2 | 0 | B | - | 2 | 0 | 2 | 1.3333 | 3.3333 | 1.3333
C | 2 | 2 | 2 | 2 | 0 | C | A,B | 2 | 3.3333 | 5.3333 | 3.3333 | 5.3333 | 0
D | 2 | 4 | 7 | 4.1667 | 0.69444 | D | C | 4.1667 | 5.3333 | 9.5 | 5.3333 | 9.5 | 0
E | 1 | 3 | 5 | 3 | 0.44444 | E | C | 3 | 5.3333 | 8.3333 | 8.5 | 11.5 | 3.1667
F | 2 | 2 | 2 | 2 | 0 | F | D,E | 2 | 9.5 | 11.5 | 14.5 | 16.5 | 5
G | 1 | 3 | 5 | 3 | 0.44444 | G | C | 3 | 5.3333 | 8.3333 | 12.5 | 15.5 | 7.1667
H | 1 | 1 | 1 | 1 | 0 | H | G | 1 | 8.3333 | 9.3333 | 15.5 | 16.5 | 7.1667
I | 2 | 5 | 8 | 5 | 1 | I | F | 5 | 11.5 | 16.5 | 11.5 | 16.5 | 0
J | 1 | 2 | 3 | 2 | 0.11111 | J | H,I | 2 | 16.5 | 18.5 | 16.5 | 18.5 | 0
K | 6 | 10 | 14 | 10 | 1.7778 | K | J | 10 | 18.5 | 28.5 | 18.5 | 28.5 | 0
Q-4.2.3 | [5 empty] | Q-4.2.4 | Since probability is 90% that is 0.90, Z = 1.29 from the Z-distribution
Critical Path |  | A-C-D-I-J-K |  |  |  | Critical Path |  | A-C-D-I-J-K
m |  | 26.5 |  |  |  | m |  | 26.5
Variance |  | 4.0278 | 2.0069 |  |  | Variance |  | 4.03 | 2.0075
X | = | 20 |  |  |  | X | = | 29.0897
Z | = | -3.2388 |  |  |  | Z | = | 1.29
P(X<=20)= |  | 0.00060022 |  |  |  | P(X<=20)= |  | 0.90147
0.060022

## Q-4.3
ESTIMATING CRASH COSTS PER DAY
| Nodes | Normal Time | Crash Time | Normal Cost | Total Crash Cost | CrashED Time | Crash cost per day
A | 1--2 | 3 | 2 | 1500 | 2500 | 1 | 1000
B | 1--4 | 2 | 2 | 1000 | 1000 | 0 | 0
C | 2--3 | 2 | 2 | 1800 | 1800 | 0 | 0
D | 3--5 | 4 | 2 | 2200 | 3200 | 2 | 500
E | 4--5 | 3 | 2 | 1600 | 2000 | 1 | 400
F | 5--7 | 2 | 2 | 800 | 800 | 0 | 0
G | 3--6 | 3 | 1 | 450 | 900 | 2 | 225
H | 6--8 | 1 | 1 | 1200 | 1200 | 0 | 0
I | 7--9 | 5 | 2 | 1450 | 2050 | 3 | 200
J | 8--10 | 2 | 1 | 450 | 900 | 1 | 450
K | 10--9 | 10 | 6 | 1800 | 4500 | 4 | 675

## Q4-3.2 LP
[5 empty] | x1 | x2 | x3 | x4 | x5 | x6 | x7 | x8 | x9 | x10
[5 empty] | 0 | 2 | 4 | 4 | 6 | 9 | 8 | 10 | 10 | 16
| Constraint | [16 empty] | Crash Costs
Max. Days A can be crashed | y12 | 1 | <= | 1 | [10 empty] | 3 | >= | 3 | y12 | 1000 | bar: x1 to x2
Max. days B can be crashed | y14 | 0 | <= | 0 | [10 empty] | 4 | >= | 2 | y14 | 0 | bar: x1; x4
Max. days C can be crashed | y23 | 0 | <= | 0 | [10 empty] | 2 | >= | 2 | y23 | 0 | bar: x2 to x3
Max. days D can be crashed | y35 | 2 | <= | 2 | [10 empty] | 4 | >= | 4 | y35 | 500 | bar: x3; x5
Max. days E can be crashed | y45 | 1 | <= | 1 | [10 empty] | 3 | >= | 3 | y45 | 400 | bar: x4 to x5
Max. days F can be crashed | y57 | 0 | <= | 0 | [10 empty] | 2 | >= | 2 | y57 | 0 | bar: x5; x7
Max. days G can be crashed | y36 | 0 | <= | 2 | [10 empty] | 5 | >= | 3 | y36 | 225 | bar: x3; x6
Max. days H can be crashed | y68 | 0 | <= | 0 | [10 empty] | 1 | >= | 1 | y68 | 0 | bar: x6; x8
Max. days I can be crashed | y79 | 3 | <= | 3 | [10 empty] | 5 | >= | 5 | y79 | 200 | bar: x7; x9
Max. days J can be crashed | y810 | 0 | <= | 1 | [10 empty] | 6 | >= | 2 | y810 | 450 | bar: x8; x10
Max. days K can be crashed | y109 | 4 | <= | 4 | [10 empty] | 10 | >= | 10 | y109 | 675 | bar: x9 to x10
[15 empty] | 2 | >= | 0 | bar: x2; x4
[15 empty] | 0 | >= | 0 | Objective | 5700 | bar: x3 to x4
[15 empty] | 0 | >= | 0 | bar: x8 to x9
[15 empty] | Complete by Dec 16th |  |  | Finish Time | 16
Constraint x10 <= 16

## Q4-3.4
[5 empty] | x1 | x2 | x3 | x4 | x5 | x6 | x7 | x8 | x9 | x10
[5 empty] | 0 | 2 | 4 | 4 | 6 | 9 | 8 | 10 | 10 | 16
| Constraint | [16 empty] | Crash Costs
Max. Days A can be crashed | y12 | 1 | <= | 1 | [10 empty] | 3 | >= | 3 | y12 | 1000 | bar: x1 to x2
Max. days B can be crashed | y14 | 0 | <= | 0 | [10 empty] | 4 | >= | 2 | y14 | 0 | bar: x1; x4
Max. days C can be crashed | y23 | 0 | <= | 0 | [10 empty] | 2 | >= | 2 | y23 | 0 | bar: x2 to x3
Max. days D can be crashed | y35 | 2 | <= | 2 | [10 empty] | 4 | >= | 4 | y35 | 500 | bar: x3; x5
Max. days E can be crashed | y45 | 1 | <= | 1 | [10 empty] | 3 | >= | 3 | y45 | 400 | bar: x4 to x5
Max. days F can be crashed | y57 | 0 | <= | 0 | [10 empty] | 2 | >= | 2 | y57 | 0 | bar: x5; x7
Max. days G can be crashed | y36 | 0 | <= | 2 | [10 empty] | 5 | >= | 3 | y36 | 225 | bar: x3; x6
Max. days H can be crashed | y68 | 0 | <= | 0 | [10 empty] | 1 | >= | 1 | y68 | 0 | bar: x6; x8
Max. days I can be crashed | y79 | 3 | <= | 3 | [10 empty] | 5 | >= | 5 | y79 | 200 | bar: x7; x9
Max. days J can be crashed | y810 | 0 | <= | 1 | [10 empty] | 6 | >= | 2 | y810 | 450 | bar: x8; x10
Max. days K can be crashed | y109 | 4 | <= | 4 | [10 empty] | 10 | >= | 10 | y109 | 675 | bar: x9 to x10
[15 empty] | 2 | >= | 0 | bar: x2; x4
[15 empty] | 0 | >= | 0 | Objective | 5300 | bar: x3 to x4
[15 empty] | 0 | >= | 0 | bar: x8 to x9
From Table 2 Q.1 -Critical Path Identified= A-C-D-I-J-K |  |  |  |  | x9: Budget Constraint | 5300 | <= | 6500 |  |  | Complete by Dec 16th
Hence, these are the critical activities we are trying to crash |  |  |  |  | x9: Finish Time; x10: Constraint x10 <= 16 | 16